## Cover Page
AI-POWERED IAM RISK ASSESSMENT
Identifying and Managing Risks in AI-Driven Identity & Access Management Systems
| Organisation | NorthBridge Financial Corp
| Industry | Financial Services / Banking
| Headquarters | Toronto, Ontario, Canada
| Size | ~2,000 employees, 3 regional offices
| AI IAM Systems | Workforce IAM Agent + Customer Authentication AI + Predictive Access Analytics
| Assessment Type | AI Risk Assessment — Second Line of Defense (2LOD)
| Frameworks Applied | NIST AI RMF · OWASP LLM Top 10 · ISO 27001:2022 A.8 · NIST SP 800-53 AC
| Regulatory Context | OSFI B-13 · PIPEDA · FINTRAC · Canadian Banking Act
| Assessor | Dhanya Mary Sam — AI Analyst, GRC & AI Governance
| Assessment Date | June 2026
| Version | v1.0
⚠ This assessment was developed for portfolio and educational purposes. NorthBridge Financial Corp is a fictional organisation. All risks, findings, and scores are illustrative.

## Executive Summary
EXECUTIVE SUMMARY — AI-POWERED IAM RISK ASSESSMENT
Risk Portfolio Overview
| Risk Level | Count | % of Total | Primary Domain | Immediate Action Required
| 🔴 Critical | 0 | 0% | AI Agent Decision Errors, Prompt Injection | Yes — immediate
| 🟠 High | 0 | 0% | Privilege Escalation, Bias, Explainability | Yes — within 30 days
| 🟡 Medium | 0 | 0% | Audit Gaps, Data Quality, Integration Failures | Within 90 days
| 🟢 Low | 0 | 0% | Documentation, Training | Ongoing
| TOTAL | 0 | 100%
Key Findings
| # | Finding |  | Severity | AI System Affected
| 1 | AI Agent making autonomous access decisions without explainability — no audit trail for why access was granted or denied |  | Critical | Workforce IAM Agent
| 2 | Prompt injection vulnerabilities in natural language IAM interfaces — attackers can manipulate AI access decisions |  | Critical | Customer Auth AI + IAM Agent
| 3 | AI model trained on historical access patterns perpetuating privilege creep — over-provisioned access normalised at scale |  | Critical | Predictive Access Analytics
| 4 | No formal AI incident response procedure for IAM failures — undefined escalation when AI agent denies mass access |  | Critical | All AI IAM Systems
| 5 | Bias in AI access recommendations — demographically correlated access denial patterns not monitored |  | High | Predictive Access Analytics
| 6 | Single point of failure — no fallback to rule-based IAM when AI agent is unavailable |  | High | Workforce IAM Agent
| 7 | Third-party AI IAM vendor has no SOC 2 Type II or AI-specific audit — supply chain risk unmanaged |  | High | All AI IAM Systems
| 8 | AI access logs not integrated into SIEM — anomalous AI decisions not visible to security operations |  | High | Workforce IAM Agent
| 9 | Customer authentication AI not subject to DPIA under PIPEDA — personal data processed without privacy review |  | High | Customer Auth AI

## AI IAM Architecture
AI IAM ARCHITECTURE — NORTHBRIDGE FINANCIAL CORP
Three AI systems operate across NorthBridge's IAM landscape, each with distinct functions, data sources, and risk profiles.
| AI System | Function | AI Type | Data Sources | Key Risk Area
| Workforce IAM Agent | Autonomous provisioning, de-provisioning, and access review for 2,000 employees and contractors. Makes real-time access grant/deny decisions. | AI Agent (Agentic AI) | HR System, Active Directory, Access Logs, Role Matrices, Behavioural Baselines | Autonomous decisions without explainability; no human-in-the-loop for high-risk grants
| Customer Authentication AI | Biometric + behavioural authentication for 180,000 retail banking customers. Detects account takeover and step-up auth triggers. | Predictive AI + AI Agent | Biometric Data, Transaction History, Device Fingerprints, Location Data, PII | PIPEDA compliance; prompt injection via natural language banking interface; false positives locking legitimate customers out
| Predictive Access Analytics | Analyses historical access patterns to recommend role assignments, flag anomalous access, and predict SoD (Segregation of Duties) violations before they occur. | Predictive AI | Access Logs, Role Definitions, HR Data, Peer Group Benchmarks, Incident History | Training data bias; privilege creep normalisation; recommendations accepted without human review
AI Types in Scope
| AI Type | Definition in IAM Context
| AI Agent | Autonomous system that perceives environment, makes decisions, and takes actions — can provision/de-provision access without human approval
| Predictive AI | Uses ML models to forecast outcomes — flags anomalous access patterns, predicts SoD violations, recommends role assignments
| Agentic AI | Multi-step reasoning agent capable of executing complex IAM workflows — combines decision-making with tool use across multiple systems

## Risk Register
AI-POWERED IAM RISK REGISTER — NORTHBRIDGE FINANCIAL CORP
| ID | Risk Description | AI System | Risk Category | Likelihood (1-5) | Impact (1-5) | Risk Score (L×I) | Severity | Recommended Control | Framework Reference
| R-01 | AI Agent makes autonomous access grant/deny decisions with no explainability — unable to audit why specific access was approved or denied, violating audit trail requirements | Workforce IAM Agent | Explainability & Auditability | 4 | 5 | 20 | Critical | Implement decision logging capturing model inputs, outputs, and confidence scores for every access decision. Require explainable AI (XAI) techniques for high-risk grants. | NIST AI RMF: GOVERN 1.7, MANAGE 2.2 ¦ ISO 27001: A.8.15 ¦ NIST 800-53: AU-2, AU-12
| R-02 | Prompt injection attack via natural language banking interface manipulates Customer Auth AI into bypassing authentication — attacker crafts malicious input to override access controls | Customer Auth AI | Prompt Injection & Adversarial Attack | 4 | 5 | 20 | Critical | Implement input validation and sanitisation for all natural language inputs. Deploy prompt injection detection layer. Red team test regularly. | OWASP LLM Top 10: LLM01 ¦ NIST AI RMF: MAP 5.1 ¦ ISO 27001: A.8.7
| R-03 | AI trained on historical access patterns normalises privilege creep — employees with historically over-provisioned access are used as peer benchmarks, perpetuating and scaling excessive access | Predictive Access Analytics | Training Data & Model Bias | 4 | 5 | 20 | Critical | Audit training datasets for privilege creep baseline. Implement regular model retraining with cleaned, least-privilege benchmarks. Human review of all access recommendations above threshold. | NIST AI RMF: MAP 2.3, MANAGE 3.1 ¦ NIST 800-53: AC-6 ¦ OSFI B-13: S.3
| R-04 | No AI-specific incident response procedure — undefined escalation path when IAM AI agent malfunctions, denies mass access, or is compromised. Traditional IR playbooks don't cover AI failure modes | All AI IAM Systems | Incident Response & Resilience | 5 | 5 | 25 | Critical | Develop AI IAM Incident Response Playbook covering: mass access denial, model poisoning, AI agent compromise, prompt injection incidents. Define escalation, containment, and rollback procedures. | NIST AI RMF: RESPOND 1.1 ¦ ISO 27001: A.5.26 ¦ NIST 800-53: IR-4, IR-9
| R-05 | AI access recommendations exhibit demographically correlated denial patterns — model may inadvertently discriminate based on features correlated with protected characteristics | Predictive Access Analytics | Algorithmic Bias & Fairness | 3 | 5 | 15 | High | Implement fairness metrics and bias monitoring in model evaluation pipeline. Regular demographic disparity analysis on access decisions. Document bias testing results. | NIST AI RMF: MAP 5.2, MEASURE 2.5 ¦ OSFI B-13: S.2 ¦ Canadian Human Rights Act
| R-06 | Single point of failure — no fallback to rule-based IAM when AI agent is unavailable. System outage causes enterprise-wide access failure affecting all 2,000 employees | Workforce IAM Agent | Resilience & Business Continuity | 3 | 5 | 15 | High | Implement rule-based IAM fallback system activated automatically on AI agent failure. Define RTO/RPO for AI IAM systems. Test failover quarterly. | ISO 27001: A.8.14 ¦ NIST 800-53: CP-10 ¦ OSFI B-13: S.4
| R-07 | Third-party AI IAM vendor has not provided SOC 2 Type II or AI-specific security audit. Supply chain risk — vendor model updates could introduce vulnerabilities without NorthBridge's knowledge | All AI IAM Systems | Third-Party & Supply Chain Risk | 3 | 5 | 15 | High | Require vendor SOC 2 Type II and AI model audit as contractual obligation. Implement change notification SLA for model updates. Annual vendor risk reassessment. | NIST AI RMF: GOVERN 6.1 ¦ ISO 27001: A.5.19 ¦ OSFI B-13: S.5
| R-08 | AI access decision logs not integrated into SIEM — anomalous AI behaviour (unusual access patterns, decision drift) invisible to security operations team | Workforce IAM Agent | Monitoring & Detection | 4 | 4 | 16 | High | Integrate AI IAM decision logs into SIEM (Microsoft Sentinel). Define alerts for access decision anomalies, volume spikes, and model confidence degradation. | ISO 27001: A.8.15, A.8.16 ¦ NIST 800-53: SI-4 ¦ NIST AI RMF: MEASURE 2.6
| R-09 | Customer Authentication AI processes biometric and behavioural PII without DPIA under PIPEDA — no privacy impact assessment conducted prior to deployment | Customer Auth AI | Privacy & Regulatory Compliance | 4 | 4 | 16 | High | Conduct PIPEDA DPIA immediately. Document lawful basis for biometric processing. Implement data minimisation. Register AI system in AI inventory. | PIPEDA ¦ ISO 27001: A.5.34 ¦ NIST AI RMF: MAP 1.6 ¦ OSFI B-13
| R-10 | AI Agent can escalate its own access permissions through chained tool calls — agentic AI accesses multiple systems sequentially, potentially accumulating privileges beyond intended scope | Workforce IAM Agent | Privilege Escalation & Agentic Risk | 3 | 5 | 15 | High | Implement strict tool-use boundaries for AI Agent. Define maximum permission scope per session. Monitor for chained access patterns. Apply least-privilege principle to AI agent identity. | OWASP LLM Top 10: LLM08 ¦ NIST AI RMF: MAP 5.5 ¦ NIST 800-53: AC-6
| R-11 | Model inversion attack — adversary queries Predictive Access Analytics repeatedly to reconstruct training data, potentially exposing HR records and sensitive access histories | Predictive Access Analytics | Adversarial Attack & Data Exposure | 2 | 5 | 10 | Medium | Implement query rate limiting and anomaly detection on model API. Apply differential privacy techniques. Monitor for systematic probing patterns. | OWASP LLM Top 10: LLM02 ¦ NIST AI RMF: MAP 5.1 ¦ ISO 27001: A.8.12
| R-12 | AI access recommendations accepted without human review for standard roles — rubber-stamping creates accountability gap where no human has assessed access grants | Predictive Access Analytics | Human Oversight & Accountability | 4 | 4 | 16 | High | Define access risk tiers requiring mandatory human review. Implement four-eyes principle for privileged role assignments. Log human review decisions. | NIST AI RMF: GOVERN 5.1 ¦ ISO 27001: A.8.2 ¦ NIST 800-53: AC-5
| R-13 | AI agent session tokens not expiring correctly — long-lived agent sessions maintain access beyond intended duration, creating persistent access risk | Workforce IAM Agent | Session Management | 3 | 4 | 12 | High | Implement strict session timeout for AI agent tokens. Apply same session management standards as human users. Monitor for long-lived sessions. | ISO 27001: A.8.5 ¦ NIST 800-53: AC-12 ¦ NIST AI RMF: MANAGE 2.4
| R-14 | Insufficient testing of AI IAM system before production deployment — no adversarial testing or red team exercise conducted on AI access controls | All AI IAM Systems | Testing & Validation | 4 | 4 | 16 | High | Implement pre-deployment adversarial testing framework. Require red team exercises specifically targeting AI IAM systems. Document test results. | NIST AI RMF: MEASURE 2.2 ¦ OWASP LLM Top 10 ¦ ISO 27001: A.8.29
| R-15 | AI model drift — Workforce IAM Agent performance degrades over time as organisational access patterns evolve, leading to increasingly inaccurate access decisions | Workforce IAM Agent | Model Performance & Drift | 3 | 4 | 12 | High | Implement continuous model performance monitoring. Define performance thresholds triggering retraining. Schedule quarterly model evaluation reviews. | NIST AI RMF: MEASURE 2.7 ¦ OSFI B-13: S.3 ¦ ISO 27001: A.8.16
| R-16 | No AI governance policy specifically covering IAM AI systems — existing IAM policy does not address AI-specific risks, responsibilities, or controls | All AI IAM Systems | Governance & Policy | 5 | 3 | 15 | High | Develop AI IAM Governance Policy covering: acceptable use, human oversight requirements, model management, incident response, and vendor management. | NIST AI RMF: GOVERN 1.1 ¦ ISO 27001: A.5.1 ¦ OSFI B-13: S.1
| R-17 | Training data includes access patterns from terminated employees not properly purged — AI recommendations influenced by stale, invalid access histories | Predictive Access Analytics | Data Quality & Integrity | 4 | 3 | 12 | High | Implement automated data purging pipeline removing terminated employee data from training sets. Validate training data quality before each model update. | ISO 27001: A.8.10 ¦ NIST AI RMF: MAP 2.3 ¦ PIPEDA
| R-18 | Customer Auth AI false positive rate too high — legitimate customers locked out during peak periods, creating customer service burden and potential OSFI complaints | Customer Auth AI | Performance & Customer Impact | 3 | 4 | 12 | High | Define acceptable false positive rate SLA. Implement real-time false positive monitoring. Create fast-track human review process for AI-locked accounts. | OSFI B-13 ¦ NIST AI RMF: MEASURE 2.5 ¦ Customer Service Standards
| R-19 | AI IAM system not included in business continuity plan — disaster recovery procedures do not account for AI model unavailability or corruption | All AI IAM Systems | Business Continuity | 3 | 4 | 12 | High | Update BCP/DRP to include AI IAM systems. Define recovery procedures for model corruption. Test AI IAM recovery scenarios annually. | ISO 27001: A.5.30 ¦ NIST 800-53: CP-2 ¦ OSFI B-13: S.4
| R-20 | Insufficient staff training on AI IAM risks — IT and security staff unaware of AI-specific failure modes, prompt injection risks, and escalation procedures | All AI IAM Systems | Training & Awareness | 4 | 3 | 12 | High | Develop AI IAM security awareness training. Include AI-specific scenarios in security training programme. Require annual completion for all IAM administrators. | NIST AI RMF: GOVERN 4.1 ¦ ISO 27001: A.6.3 ¦ OSFI B-13: S.2
| R-21 | No SoD (Segregation of Duties) controls applied to AI IAM system administration — same team builds, deploys, and monitors AI models without independent oversight | All AI IAM Systems | Segregation of Duties | 3 | 4 | 12 | High | Implement SoD for AI IAM administration. Separate model development, deployment, and monitoring roles. Require independent review for model updates. | ISO 27001: A.5.3 ¦ NIST 800-53: AC-5 ¦ NIST AI RMF: GOVERN 5.2
| R-22 | AI agent API not rate-limited — adversary can query AI IAM agent at scale to probe access decision logic and map permission boundaries | Workforce IAM Agent | API Security | 3 | 3 | 9 | Medium | Implement API rate limiting on AI IAM agent endpoints. Monitor for unusual query patterns. Require authentication for all API calls. | OWASP LLM Top 10: LLM04 ¦ ISO 27001: A.8.20 ¦ NIST 800-53: SC-5
| R-23 | AI model weights stored without encryption — if storage is compromised, adversary could extract, copy, or modify model weights | All AI IAM Systems | Model & Data Security | 2 | 4 | 8 | Medium | Encrypt AI model weights at rest and in transit. Implement access controls on model storage. Log all model access events. | ISO 27001: A.8.24 ¦ NIST 800-53: SC-28 ¦ NIST AI RMF: MANAGE 2.4
| R-24 | No formal AI risk register maintained — AI IAM risks not tracked, owned, or reviewed on a scheduled basis | All AI IAM Systems | Risk Management | 5 | 3 | 15 | High | Establish and maintain AI risk register (this document). Assign risk owners. Schedule quarterly risk reviews. Integrate with enterprise risk management framework. | NIST AI RMF: GOVERN 1.4 ¦ ISO 27001: Clause 6.1 ¦ OSFI B-13
| R-25 | Customer Auth AI vendor retains biometric data for model training without explicit customer consent — potential PIPEDA violation and reputational risk | Customer Auth AI | Privacy & Consent | 3 | 4 | 12 | High | Review vendor data processing agreement. Require explicit consent for biometric model training. Implement data deletion rights process. | PIPEDA ¦ GDPR (for international customers) ¦ ISO 27001: A.5.34

## Control Mapping
CONTROL MAPPING — AI IAM RISK CONTROLS vs FRAMEWORKS
| Risk ID | Control | NIST AI RMF | OWASP LLM Top 10 | ISO 27001:2022 | NIST SP 800-53
| R-01 | AI Decision Logging & XAI | GOVERN 1.7, MANAGE 2.2 | LLM06 (Sensitive Info) | A.8.15 (Logging) | AU-2, AU-12
| R-02 | Prompt Injection Prevention | MAP 5.1 | LLM01 (Prompt Injection) | A.8.7 (Malware Protection) | SI-10, SI-15
| R-03 | Training Data Governance | MAP 2.3, MANAGE 3.1 | LLM03 (Training Data) | A.8.10 (Info Deletion) | AC-6, SA-9
| R-04 | AI Incident Response Playbook | RESPOND 1.1, 1.2 | LLM09 (Overreliance) | A.5.26 (IR Planning) | IR-4, IR-8, IR-9
| R-05 | Bias & Fairness Monitoring | MAP 5.2, MEASURE 2.5 | LLM09 | A.5.2 (IS Roles) | SA-11, PM-26
| R-06 | Rule-Based Fallback System | MANAGE 2.4 | LLM08 (Excessive Agency) | A.8.14 (Redundancy) | CP-10, CP-13
| R-07 | Vendor AI Risk Assessment | GOVERN 6.1, 6.2 | LLM05 (Supply Chain) | A.5.19, A.5.20 | SA-9, SA-12
| R-08 | SIEM Integration for AI Logs | MEASURE 2.6 | LLM06 | A.8.15, A.8.16 | SI-4, AU-6
| R-09 | PIPEDA DPIA for Biometric AI | MAP 1.6 | LLM06 | A.5.34 (Privacy) | PT-2, PT-3
| R-10 | AI Agent Least Privilege | MAP 5.5 | LLM08 (Excessive Agency) | A.8.2 (Privileged Access) | AC-6, AC-17
| R-11 | Model API Rate Limiting | MAP 5.1 | LLM02 (Insecure Output) | A.8.20 (Network Security) | SC-5, AC-17
| R-12 | Human Review for High-Risk Access | GOVERN 5.1 | LLM08 | A.8.2, A.5.3 | AC-5, PE-2
| R-13 | AI Session Token Management | MANAGE 2.4 | LLM08 | A.8.5 (Auth) | AC-12, IA-11
| R-14 | Adversarial Testing Programme | MEASURE 2.2 | All LLM Top 10 | A.8.29 (Secure Dev) | SA-11, RA-5
| R-15 | Model Drift Monitoring | MEASURE 2.7 | LLM09 | A.8.16 (Monitoring) | SI-4, CA-7
| R-16 | AI IAM Governance Policy | GOVERN 1.1 | N/A | A.5.1 (Policies) | PM-9, PL-1
| R-17 | Training Data Quality Controls | MAP 2.3 | LLM03 | A.8.10 | SI-12, SA-8
| R-18 | False Positive Rate SLA | MEASURE 2.5 | LLM09 | A.8.16 | PM-16, IR-5
| R-19 | BCP Update for AI Systems | MANAGE 2.4 | N/A | A.5.30 (BCP) | CP-2, CP-4
| R-20 | AI Security Awareness Training | GOVERN 4.1 | N/A | A.6.3 (Awareness) | AT-2, AT-3
| R-21 | SoD for AI Administration | GOVERN 5.2 | N/A | A.5.3 (SoD) | AC-5, PS-7
| R-22 | AI API Rate Limiting | MAP 5.1 | LLM04 (DoS) | A.8.20 | SC-5
| R-23 | AI Model Encryption | MANAGE 2.4 | LLM02 | A.8.24 (Encryption) | SC-28, SC-8
| R-24 | AI Risk Register Maintenance | GOVERN 1.4 | N/A | Clause 6.1 | RA-3, PM-28
| R-25 | Vendor Data Processing Agreement | GOVERN 6.1 | LLM06 | A.5.34 | PT-7, SA-9

## Remediation Roadmap
REMEDIATION ROADMAP — PRIORITISED ACTION PLAN
PHASE 1 — IMMEDIATE (Month 1)
| Risk ID | Action | Owner | Timeline | Priority
| R-04 | Develop AI IAM Incident Response Playbook | CISO + AI Team | Month 1 | Critical
| R-16 | Draft and approve AI IAM Governance Policy | Chief Risk Officer | Month 1 | Critical
| R-01 | Implement AI decision logging and audit trail | AI Engineering | Month 1 | Critical
| R-02 | Deploy prompt injection detection and input validation | Security Engineering | Month 1 | Critical
| R-06 | Design and test rule-based IAM fallback system | IAM Team | Month 1 | Critical
PHASE 2 — SHORT TERM (Month 2-3)
| Risk ID | Action | Owner | Timeline | Priority
| R-09 | Conduct PIPEDA DPIA for Customer Auth AI | Privacy Officer | Month 2 | High
| R-07 | Issue vendor AI security audit requirement | Procurement + Risk | Month 2 | High
| R-08 | Integrate AI decision logs into Microsoft Sentinel SIEM | Security Operations | Month 2 | High
| R-10 | Implement least-privilege controls for AI Agent identity | IAM Team | Month 2 | High
| R-03 | Audit and clean training data — remove privilege creep baselines | AI Engineering | Month 3 | Critical
| R-12 | Define access risk tiers and human review workflow | IAM + Risk Team | Month 3 | High
| R-14 | Commission adversarial testing of AI IAM systems | Security Team | Month 3 | High
PHASE 3 — MEDIUM TERM (Month 4-6)
| Risk ID | Action | Owner | Timeline | Priority
| R-05 | Implement bias monitoring and fairness metrics | AI Engineering + HR | Month 4 | High
| R-15 | Deploy model drift monitoring and retraining pipeline | AI Engineering | Month 4 | High
| R-13 | Fix AI agent session token expiry controls | IAM Team | Month 4 | Medium
| R-17 | Implement automated training data purging pipeline | Data Engineering | Month 5 | Medium
| R-18 | Define and monitor false positive rate SLA | AI Engineering | Month 5 | Medium
| R-19 | Update BCP/DRP to include AI IAM systems | BCM Team | Month 5 | Medium
| R-21 | Implement SoD for AI IAM administration | HR + Risk | Month 6 | Medium
| R-24 | Establish AI risk register ownership and review cycle | Risk Management | Month 6 | High
PHASE 4 — ONGOING
| Risk ID | Action | Owner | Timeline | Priority
| R-11 | Monitor model API for probing and rate limit enforcement | Security Operations | Ongoing | Medium
| R-20 | Deliver AI security awareness training to IAM admins | L&D + Security | Ongoing | Medium
| R-22 | API rate limiting review and tuning | Security Engineering | Ongoing | Low
| R-23 | Model encryption and access control audit | Security Team | Ongoing | Medium
| R-25 | Annual vendor data processing agreement review | Procurement + Privacy | Ongoing | Medium